## Sheet1
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week) | [6 empty] | Week #5 (10 hrs / week) | [6 empty] | Week #6 (10 hrs / week) | [6 empty] | Week #7 (10 hrs / week) | [6 empty] | Week #8 (10 hrs / week) | [6 empty] | Week #9 (10 hrs / week) | [6 empty] | Week #10 (10 hrs / week) | [6 empty] | Week #11 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 1) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7
 | time axis 2020-02-24 to 2020-05-09
40
week1: Analysis requirement | Read project requirement. Learn potential technology that may helpful. Familiar with MongoDB, graphql, and flack. | Yanlin Song | 10 | 2020-02-25: 2; 2020-02-27: 3; 2020-03-01: 5
|  | Xuejun Yao | 10 | 2020-02-24: 2
|  | Shengtao LI | 10 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-29: 2; 2020-03-01: 4
|  | Kuang Sheng | 10 | 2020-02-25: 2; 2020-02-27: 3; 2020-02-28: 3; 2020-02-29: 2
week 2:Design schema | Learn ariadny graphql schema format | Yanlin Song | 10 | 2020-03-02: 2; 2020-03-03: 2; 2020-03-07: 3; 2020-03-08: 3
| Read the requireement and design classes | Xuejun Yao | 10 | 2020-03-03: 2; 2020-03-04: 1; 2020-03-07: 3; 2020-03-08: 4
| Search example and prepare database | Shengtao LI | 10 | 2020-03-02: 3; 2020-03-03: 2; 2020-03-07: 2; 2020-03-08: 3
| Learn graphql sehcma | Kuang Sheng | 10 | 2020-03-02: 2; 2020-03-03: 2; 2020-03-06: 3; 2020-03-07: 3
week 3:Mongodb | connect to mongodb atlas, and add some data to db | Yanlin Song | 10 | bar: 2020-03-09 to 2020-03-15
| reserch mongodb lib that work with python | Xuejun Yao | 10 | 2020-03-10: 3; 2020-03-12: 2; 2020-03-14: 2; 2020-03-15: 3
| write script to inject car into local or online db | Shengtao LI | 10 | bar: 2020-03-09 to 2020-03-15
| build local db with gui, and study library | Kuang Sheng | 10 | 2020-03-10: 2; 2020-03-11: 2; 2020-03-12: 3; 2020-03-13: 3
week 4: Backend server | follow up the corrent progress, write script for query and mutation | Yanlin Song | 10 | 2020-03-16: 2; 2020-03-17: 2; 2020-03-18: 2; 2020-03-20: 2; 2020-03-22: 2
| Build schema with Location, booking, and contract | Xuejun Yao | 10 | 2020-03-17: 2; 2020-03-18: 2; 2020-03-21: 3; 2020-03-22: 3
| using flask and graphql playground build a workable server | Shengtao LI | 10 | bar: 2020-03-16 to 2020-03-22
| set query field and mutation field | Kuang Sheng | 10 | 2020-03-17: 3; 2020-03-18: 3; 2020-03-20: 3; 2020-03-21: 1
week 5:Backend server | write resolver for check availibity of a car | Yanlin Song | 10 | 2020-03-23: 3; 2020-03-27: 1; 2020-03-28: 3; 2020-03-29: 3
| keep finish the graphql api for query and mutation | Xuejun Yao | 10 | 2020-03-24: 1; 2020-03-25: 3; 2020-03-26: 1; 2020-03-29: 5
| prototyping frontend | Shengtao LI | 10 | bar: 2020-03-23 to 2020-03-29
| get in touch with the frontend Nodejs | Kuang Sheng | 10 | 2020-03-24: 2; 2020-03-25: 2; 2020-03-26: 2; 2020-03-27: 3; 2020-03-28: 1
week 6: Frontend start, and backend | write get availiable time function in give user interval | Yanlin Song | 10 | 2020-04-03: 3; 2020-04-04: 3; 2020-04-05: 4
| Learn header and other authentication example | Xuejun Yao | 10 | 2020-04-01: 2; 2020-04-02: 3; 2020-04-04: 4; 2020-04-05: 1
| Script for vehicle types, and injest location | Shengtao LI | 10 | bar: 2020-03-30 to 2020-04-05
| Learning javascript and react | Kuang Sheng | 10 | 2020-03-30: 1; 2020-03-31: 4; 2020-04-02: 2; 2020-04-03: 3
week 7: Frontend backend | write car searching algorithem. | Yanlin Song | 10 | 2020-04-06: 2; 2020-04-07: 2; 2020-04-10: 2; 2020-04-11: 2; 2020-04-12: 2
| add graphql funtion for getting user info aster login | Xuejun Yao | 10 | 2020-04-07: 1; 2020-04-08: 3; 2020-04-10: 4; 2020-04-11: 2
| authentication, UI libraries, and initial UI wireframe | Shengtao LI | 10 | bar: 2020-04-06 to 2020-04-12
| coding for lication, and get 200 location geo data | Kuang Sheng | 10 | 2020-04-06: 3; 2020-04-07: 3; 2020-04-08: 3; 2020-04-09: 1
week 8: Frontend backend | update car search algo, if no availiable car, search near location | Yanlin Song | 10 | 2020-04-18: 5; 2020-04-19: 5
| Display info on the different pages. | Xuejun Yao | 10 | 2020-04-14: 1; 2020-04-16: 1; 2020-04-18: 3; 2020-04-19: 5
| add comment feature, and vehicle search front end | Shengtao LI | 10 | 2020-04-13: 2; 2020-04-18: 4; 2020-04-19: 4
| add 200 geo data, use google api show red mark on map | Kuang Sheng | 10 | 2020-04-14: 4; 2020-04-15: 2; 2020-04-16: 4
week 9: frontend, backend, and testing | Remove booking and contract in model, combine with reservation | Yanlin Song | 10 | 2020-04-25: 5; 2020-04-26: 5
| Frontend, display information. Connect front end with graphql | Xuejun Yao | 10 | 2020-04-21: 2; 2020-04-23: 3; 2020-04-24: 4; 2020-04-26: 1
| add comment feature, and vehicle search front end | Shengtao LI | 10 | 2020-04-20: 2; 2020-04-21: 1; 2020-04-25: 4; 2020-04-26: 3
| calculate distance between points, learn from different examples | Kuang Sheng | 10 | 2020-04-21: 1; 2020-04-22: 3; 2020-04-24: 3; 2020-04-25: 2; 2020-04-26: 1
week 10: bug checking, read for report | add parameter table, update payment calculation | Yanlin Song | 10 | 2020-04-30: 1; 2020-05-01: 3; 2020-05-02: 2; 2020-05-03: 4
| write membership renew page | Xuejun Yao | 10 | 2020-04-28: 1; 2020-04-30: 3; 2020-05-02: 2; 2020-05-03: 4
| vehicle detail page, admin function polish, AWS autoscaling research | Shengtao LI | 10 | 2020-04-27: 2; 2020-04-30: 2; 2020-05-02: 3; 2020-05-03: 3
| Frontend page, display user information | Kuang Sheng | 10 | 2020-04-27: 1; 2020-04-28: 3; 2020-04-29: 3; 2020-04-30: 3
week 11: chart, ppt, test cases | Integrating all section. PPT. Prepare for the presentation. Prepare test cases. Deploy to AWS, Record video for backup | Yanlin Song | 10 | 2020-05-04: 2; 2020-05-05: 2; 2020-05-06: 2; 2020-05-07: 2; 2020-05-08: 2
|  | Xuejun Yao | 10 | 2020-05-05: 2; 2020-05-06: 4; 2020-05-08: 4
|  | Shengtao LI | 10 | 2020-05-07: 4; 2020-05-08: 4; 2020-05-09: 2
|  | Kuang Sheng | 10 | 2020-05-05: 4; 2020-05-06: 4; 2020-05-07: 2
440
Team:
Yanlin Song | 10 hours / Week
Xuejun Yao | 10 hours / Week
Shengtao LI | 10 hours / Week
Kuang Sheng | 10 hours / Week
Total Available Hours During Sprint: | 440
Ideal Burndown
Remaining Hrs (Total)